## Sheet1
DATE | THINGS TO BE DONE | Status | comments | work assigned to sumanth | work done by sumanth | work assigned to bhargav | work done by bhargav
sept-6 to sept 13 | algorithm study | done |  | 1) find the best service providers suitable to our project like aws etc | hosting raja--prefered aws--above 1 lac users | here maps and mapping logics | done
sept 13 to sept 27 | mapping part | done |  | find best database servers providers |  | study mappping | done
sppt 27 to sept 30 | mapping part | done |  |  |  | storing map related data in database
sept 30 to oct 11 | mapping part and looking for generating income like adds and sponcers | done
oct 25 to nov 1 | chaT BOT basic | on going
nov 2 to nov 8 | chaT BOT with phone number hide
oct 25 to nov 8 | payment gateway and api | yet to start
nov 8 to nov 22 | user interface | yet to start
nov 22 to nov 29 | buffer | yet to start
nov 29 to dec 31 | testing stage | yet to start
jan 1 2020 | deployment of project | yet to start
on going
yet to start
over due
done