## Sheet1
DATE | THINGS TO BE DONE | Status | comments | work assigned to sumanth | work done by sumanth | work assigned to bhargav | work done by bhargav
sept-6 to sept 13 | algorithm study | on going |  | 1) find the best service providers suitable to our project like aws etc |  | study sride algo if time permits study quick ride algo also
sept 13 to oct 11 | mapping part | yet to start
oct 11 to oct 25 | chaT BOT | yet to start
oct 25 to nov 8 | payment gateway and api | yet to start
nov 8 to nov 22 | user interface | yet to start
nov 22 to nov 29 | buffer | yet to start
nov 29 to dec 31 | testing stage | yet to start
jan 1 2020 | deployment of project | yet to start
on going
yet to start
over due